## Timeline
Grab UC4 Benchmark Scope Edition: delivery timeline (2 senior devs, 1 junior dev, SA/QA)
Project start (Monday) |  | 2026-10-07 |  | Edit only blue cells (Start Day, Duration, Owner). Everything else is calculated.
[10 empty] | Legend | Dev A |  |  | Dev B |  |  | Jr Dev |  |  | Aryo (SA/QA) |  |  | Joint |  |  | Milestone
[11 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5
[10 empty] | Working day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID | Week | Workstream | Task | Owner | Start Day | Duration (days) | End Day | Start Date | End Date | Notes | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10
1.1 | Week 1 | Setup | Kickoff, Cognigy project, Voice Gateway WebRTC client endpoint | Dev A | 1 | 1 | 1 | 2026-10-07 | 2026-10-07
1.2 | Week 1 | Setup | Code: Config (phase values), Config (steps) node, language packs node (en only), Code: Initiate, Once and greeting | Dev A | 2 | 2 | 3 | 2026-10-08 | 2026-10-09 | TDD 6.3, 6.5
1.3 | Week 1 | Setup | Sprint 0: actions.output reaches the agent (OI-19); STT hears English and Malay together (OI-23) | Dev A | 4 | 1 | 4 | 2026-10-12 | 2026-10-12
1.4 | Week 1 | Setup | AI Agent node skeleton, tool shells with guards, shared helper pattern | Dev B | 1 | 2 | 2 | 2026-10-07 | 2026-10-08 | TDD 6.1 to 6.3
1.5 | Week 1 | Onboarding | Jr Dev onboarding: Cognigy basics, TDD walkthrough, conventions | Jr Dev | 1 | 1 | 1 | 2026-10-07 | 2026-10-07 | Led by Dev B.
1.6 | Week 1 | Setup | Step catalogue data entry (reviewed by Dev B by day 4) | Jr Dev | 2 | 3 | 4 | 2026-10-08 | 2026-10-12 | TDD 6.6
1.9 | Week 1 | Testing | Unit test sheet per tool from TDD Section 6 decision tables | Aryo (SA/QA) | 3 | 2 | 4 | 2026-10-09 | 2026-10-12
M1 | Week 1 | Milestone | Slice 1 done: WebRTC call reaches the AI Agent, greets and closes | Milestone | 4 | 1 | 4 | 2026-10-12 | 2026-10-12
2.1 | Week 1 | Slice 2 | resolve_order_age (Band 1 features) | Dev A | 5 | 2 | 6 | 2026-10-13 | 2026-10-14 | TDD 6.7
2.2 | Week 2 | Slice 2 | get_approved_answer: further_inquiry and out_of_scope | Dev A | 7 | 1 | 7 | 2026-10-15 | 2026-10-15 | TDD 6.8
2.3 | Week 2 | Slice 1 | end_call (closing_a), Code: Build ACW, Code: Mock Transfer (reviewed by Dev A) | Jr Dev | 7 | 3 | 9 | 2026-10-15 | 2026-10-19 | TDD 6.12, 6.14
2.4 | Week 2 | Slice 2 | AI Agent job instructions v1 and parameters | Dev A | 8 | 2 | 9 | 2026-10-16 | 2026-10-19 | TDD 6.15
2.5 | Week 1 | Slice 3 | start_walkthrough (status, submit, status_then_submit; GrabMart rules) | Dev B | 3 | 2 | 4 | 2026-10-09 | 2026-10-12 | TDD 6.10
2.6 | Week 1 | Slice 3 | advance_walkthrough core: confirmed, status outcomes, History fallback, submitted, yes and no, needs_time | Dev B | 5 | 4 | 8 | 2026-10-13 | 2026-10-16 | TDD 6.11. Critical path.
2.7 | Week 1 | Setup | WebRTC test page with LOB and language selectors | Jr Dev | 5 | 2 | 6 | 2026-10-13 | 2026-10-14 | Reviewed by Dev A.
2.8 | Week 1 | Testing | Unit test each tool as it lands; review Jr Dev code paths | Aryo (SA/QA) | 5 | 4 | 8 | 2026-10-13 | 2026-10-16
2.9 | Week 2 | Testing | Slice 2 text run: TC-001, 002, 004, 025, 026, 028 | Aryo (SA/QA) | 9 | 1 | 9 | 2026-10-19 | 2026-10-19
M2 | Week 2 | Milestone | Slice 2 pass: six timeline cases | Milestone | 9 | 1 | 9 | 2026-10-19 | 2026-10-19
3.1 | Week 2 | Slice 4 | advance_walkthrough exceptions: repeat, link_not_found, route 1, scroll and role path | Dev B | 9 | 2 | 10 | 2026-10-19 | 2026-10-20
3.2 | Week 2 | Slice 4 | transfer_to_live_agent (mock) decision; out_of_scope offer wiring | Dev A | 10 | 1 | 10 | 2026-10-20 | 2026-10-20 | TDD 6.12
3.3 | Week 3 | Voice | Set Session Config: English primary, Malay alternate, phrase hints, barge-in; silence handling | Dev B | 11 | 1 | 11 | 2026-10-21 | 2026-10-21 | TDD 6.3
3.4 | Week 2 | Testing | Slice 3 text run: TC-003, 005, 027, 029 | Aryo (SA/QA) | 10 | 2 | 11 | 2026-10-20 | 2026-10-21
3.5 | Week 2 | Testing | Execute slice text cases and record evidence (Date, Session ID, Status) | Jr Dev | 10 | 3 | 12 | 2026-10-20 | 2026-10-22 | Aryo reviews transcripts.
3.6 | Week 3 | Config | Apply Grab answers to Code: Config flags and wording | Joint | 11 | 1 | 11 | 2026-10-21 | 2026-10-21 | Aryo plus Dev A.
3.7 | Week 3 | Testing | Slice 4 text run: TC-006 to TC-010 | Aryo (SA/QA) | 12 | 1 | 12 | 2026-10-22 | 2026-10-22
M3 | Week 3 | Milestone | Band 1 feature complete | Milestone | 12 | 1 | 12 | 2026-10-22 | 2026-10-22
3.8 | Week 3 | Fixes | Defect fixes and prompt tuning | Dev A | 11 | 3 | 13 | 2026-10-21 | 2026-10-23
3.9 | Week 3 | Fixes | Defect fixes | Dev B | 12 | 2 | 13 | 2026-10-22 | 2026-10-23
3.10 | Week 3 | Testing | Full text pass: all 15 benchmark cases | Aryo (SA/QA) | 13 | 1 | 13 | 2026-10-23 | 2026-10-23
3.11 | Week 3 | Testing | Regression on cases already passed | Jr Dev | 13 | 1 | 13 | 2026-10-23 | 2026-10-23
M4 | Week 3 | Milestone | 15 benchmark cases pass as text | Milestone | 13 | 1 | 13 | 2026-10-23 | 2026-10-23
4.1 | Week 3 | Voice | WebRTC browser and audio check: browsers, headset vs laptop speakers | Aryo (SA/QA) | 13 | 1 | 13 | 2026-10-23 | 2026-10-23
4.2 | Week 3 | Testing | Voice runs over WebRTC: 15 benchmark cases, with Manglish turns | Aryo (SA/QA) | 14 | 2 | 15 | 2026-10-26 | 2026-10-27 | Jr Dev runs half the sessions.
4.3 | Week 3 | Testing | Support voice runs and record evidence | Jr Dev | 15 | 2 | 16 | 2026-10-27 | 2026-10-28
4.4 | Week 3 | Fixes | Voice fixes: ASR hints, barge-in, timeouts, prompt tuning | Dev A | 14 | 2 | 15 | 2026-10-26 | 2026-10-27
4.5 | Week 3 | Fixes | Voice fixes: Manglish recognition and walkthrough edge cases | Dev B | 14 | 2 | 15 | 2026-10-26 | 2026-10-27
4.6 | Week 4 | Testing | Benchmark dry run: 15 cases, 3 runs each | Aryo (SA/QA) | 16 | 2 | 17 | 2026-10-28 | 2026-10-29 | About 45 sessions.
4.7 | Week 4 | Band 2 | resolve_order_age Band 2: unclear date, correction, second order | Dev A | 16 | 2 | 17 | 2026-10-28 | 2026-10-29 | Built only after M4.
4.8 | Week 4 | Band 2 | advance_walkthrough Band 2: full stuck ladder, routes 2 and 3 with soft close, view order journey | Dev B | 16 | 2 | 17 | 2026-10-28 | 2026-10-29
4.9 | Week 4 | Testing | Support dry run | Jr Dev | 17 | 1 | 17 | 2026-10-29 | 2026-10-29
4.10 | Week 4 | Benchmark | Grab benchmark run on the WebRTC link, hotfix standby | Joint | 18 | 1 | 18 | 2026-10-30 | 2026-10-30 | All four.
M5 | Week 4 | Milestone | Benchmark completed | Milestone | 18 | 1 | 18 | 2026-10-30 | 2026-10-30
5.1 | Week 4 | Band 2 | get_approved_answer Band 2: dissatisfied, human_request, language_request, other topics | Dev A | 19 | 2 | 20 | 2026-11-02 | 2026-11-03
5.2 | Week 5 | Band 2 | escalate_safety; end_call other exit types | Dev A | 21 | 1 | 21 | 2026-11-04 | 2026-11-04
5.3 | Week 4 | Band 2 | platform_switch, skip_to_step; Band 2 defect fixes | Dev B | 19 | 3 | 21 | 2026-11-02 | 2026-11-04
5.4 | Week 4 | Testing | Band 2 text runs: TC-011 to TC-024, TC-030 to TC-045, with evidence | Jr Dev | 19 | 4 | 22 | 2026-11-02 | 2026-11-05 | Aryo reviews.
5.5 | Week 4 | Testing | Band 2 review, TC-023 and TC-024 (ask_then_transfer), voice sample, phase report | Aryo (SA/QA) | 19 | 4 | 22 | 2026-11-02 | 2026-11-05
5.6 | Week 5 | Fixes | Band 2 defect fixes | Dev A | 22 | 1 | 22 | 2026-11-05 | 2026-11-05
M6 | Week 5 | Milestone | Band 2 tested, phase closed | Milestone | 22 | 1 | 22 | 2026-11-05 | 2026-11-05
|  |  | Benchmark run (working day) |  | 18
|  |  | Benchmark run date |  | 2026-10-30
|  |  | Phase closed (working day) |  | 22
|  |  | Phase closed date |  | 2026-11-05

## Effort
Build effort by work package (Benchmark Scope Edition)
Dev days are senior equivalent. Jr Dev factor converts them to junior calendar days.
Jr Dev factor | 1.5
Work package | Band | Owner | Dev days (senior equivalent) | TDD section
WebRTC client endpoint | 1 | Dev A | 0.5 | 6.3
Config nodes, Code: Initiate, start up flow | 1 | Dev A | 2 | 6.3, 6.5
Sprint 0 checks | 1 | Dev A | 0.5 | 6.3
resolve_order_age (Band 1) | 1 | Dev A | 1.5 | 6.7
get_approved_answer (further_inquiry, out_of_scope) | 1 | Dev A | 1 | 6.8
transfer_to_live_agent decision | 1 | Dev A | 0.5 | 6.12
AI Agent instructions and prompt tuning | 1 | Dev A | 3 | 6.15
AI Agent skeleton, guards, helpers | 1 | Dev B | 1.5 | 6.1 to 6.3
start_walkthrough | 1 | Dev B | 1 | 6.10
advance_walkthrough core | 1 | Dev B | 3 | 6.11
advance_walkthrough exceptions | 1 | Dev B | 1.5 | 6.11
Set Session Config and silence handling | 1 | Dev B | 1 | 6.3
Step catalogue data entry | 1 | Jr Dev | 1 | 6.6
WebRTC test page | 1 | Jr Dev | 0.5 | 6.3
end_call, Build ACW, Mock Transfer | 1 | Jr Dev | 1.5 | 6.12, 6.14
resolve_order_age (Band 2) | 2 | Dev A | 1 | 6.7
get_approved_answer (Band 2 topics, language) | 2 | Dev A | 1.5 | 6.8
escalate_safety, end_call exits | 2 | Dev A | 0.5 | 6.13, 6.14
advance_walkthrough Band 2 branches | 2 | Dev B | 1.5 | 6.11
platform_switch, skip_to_step | 2 | Dev B | 1 | 6.11
search_knowledge and knowledge content | 3 | none | 0 | Deferred
Malay content pack (Tier 1 translation) | 3 | none | 0 | Not in scope
Summary | Dev days
Band 1 total | 20
Band 2 total | 5.5
Dev A | 12
Dev B | 10.5
Jr Dev (senior equivalent) | 3
Jr Dev (calendar, with factor) | 4.5

## Assumptions and Risks
Assumptions and risks
Type | ID | Item | Impact
Assumption | A1 | Scope follows the TDD Benchmark Scope Edition: Band 1 (15 benchmark cases) is the acceptance gate; Band 2 is built after the 15 cases pass as text and tested after the benchmark. | Benchmark on day 18; phase closes on day 22.
Assumption | A2 | No translation of English content into Bahasa Melayu: no Malay content pack and no Malay test case set. Knowledge search stays deferred. | Removes about 4 days of drafting, approval and Malay test runs. Fixed Tier 1 lines stay in English.
Assumption | A3 | The bot still understands Bahasa Melayu and Manglish (STT hears both; tool descriptions carry Malay words). Guided replies may follow the merchant's wording, but fixed lines (timeline, steps, closings) are spoken in English. | Agree this with Grab; it matters if merchants reply mostly in Malay.
Assumption | A4 | TC-023 and TC-024 run with languageSwitch = ask_then_transfer, as SRC-4 describes them.
Assumption | A5 | WebRTC voice client only; transfer is a mock with the ACW written to the log.
Assumption | A6 | Two senior Cognigy developers full time. The junior developer takes about 1.5 times a senior's time and works only on well specified tasks off the critical path, reviewed by a senior. | Seniors spend about half a day per week on reviews, absorbed in their durations.
Assumption | A7 | Aryo is solution architect and QA lead; the junior developer executes scripted text cases and records evidence, Aryo reviews transcripts.
Assumption | A8 | Each benchmark case passes 3 runs in the dry run. | About 45 WebRTC sessions on days 16 and 17.
Risk | R1 | Grab does not accept the WebRTC call or the mock transfer for TC-009 and TC-010 (OI-24). | Agree in writing in week 1.
Risk | R2 | Merchants answer mostly in Bahasa Melayu while fixed lines stay in English. | Raise with Grab now. Adding the Malay content pack later adds about 4 to 5 days.
Risk | R3 | STT accuracy on Manglish is weak. | Checked on day 4. Phrase hints, Malay alternate language, or another STT vendor.
Risk | R4 | advance_walkthrough core takes longer than 4 days. | Critical path for slices 3 and 4; start testing the confirmed path early.
Risk | R5 | Step catalogue review slips past day 4. | Dev B depends on it for slice 3.
Risk | R6 | Grab answers on TC-027 (OI-03) or TC-006 (OI-13) arrive late. | Config only, but they must land before the voice runs on day 14.